PROJECT CHARTER & SCHEDULE

Autonomous Mobile Robot (AMR) Development

with Integrated C++ for ROS 2 Learning Track

ROS 2 Jazzy Jalisco  ·  Gazebo Harmonic  ·  ESP32 + RPLIDAR A1M8

Prepared following the Google Project Management Certificate framework

Document Version: 2.0   ·   April 2026   ·   Duration: 24 weeks

Changes from v1.0: added C++ learning track (G5, WBS 6.0), new milestones L1–L3, updated Gantt

# Part 1 — Project Charter

## 1.1  Project Summary

This project develops an Autonomous Mobile Robot (AMR) capable of 2D mapping (SLAM), localization on a known map (AMCL), and autonomous point-to-point navigation (Nav2) in an indoor environment. The platform is a three-wheel differential-drive chassis controlled by an ESP32 microcontroller, sensed by an RPLIDAR A1M8 laser scanner, and orchestrated by a PC running ROS 2 Jazzy Jalisco on Ubuntu 24.04 with Gazebo Harmonic for simulation.

Development is simulation-first: the navigation stack is validated in Gazebo Harmonic before any code runs on physical hardware. The second half of the project ports the validated stack to the ESP32 + diff-drive platform over WiFi (UDP for motor/odometry, TCP for LiDAR tunneling).

Version 2 of the charter adds an integrated C++ for ROS 2 learning track that runs in parallel with the main project from Week 3 to Week 20. The learning track is structured so that it never sits on the critical path — if C++ practice falls behind, main-project delivery is unaffected. The culminating C++ deliverable (WBS 4.5) is a hardware-compatible port of the Python UDP bridge that can replace the Python node at the end of the project.

## 1.2  Project Goals (SMART)

Five goals. G5 is the new C++ learning goal introduced in v2.

| # | Goal | SMART Criteria |
| --- | --- | --- |
| G1 | Build a fully simulated AMR in Gazebo Harmonic that autonomously navigates to goals | S: diff-drive + LiDAR in a custom world. M: 10 consecutive goals reached without collision. A: existing URDF + Nav2 defaults. R: foundation for hardware port. T: Week 14. |
| G2 | Produce a reusable 2D occupancy map of the target indoor environment with slam_toolbox | S: .pgm + .yaml. M: ≥ 95% floor area, < 5 cm wall thickness error. A: slam_toolbox async + teleop. R: prerequisite for AMCL. T: Week 16. |
| G3 | Achieve autonomous Nav2 navigation on hardware with localization error below 10 cm | S: Nav2 stack on ESP32 platform. M: AMCL pose error < 10 cm over 5 goals. A: hardware and stack independently validated. R: central deliverable. T: Week 22. |
| G4 | Deliver a reproducible project repository with complete documentation | S: Git repo + README + arch. diagram + launch files + YAMLs. M: second engineer reproduces system from README alone in < 2 hours. A: drafts exist. R: enables extension. T: Week 24. |
| G5 | Become competent in C++ for ROS 2 over the course of this project | S: ≥ 7 C++ programs (2 non-ROS + 5 rclcpp nodes) plus 1 production hardware node. M: final C++ UDP bridge matches Python behavior on 1-hour test. A: paced in 2-week blocks. R: closes the language gap for Nav2 source-reading and custom plugins. T: Week 20. |

## 1.3  Deliverables

### Primary Deliverables

- Validated Gazebo Harmonic simulation with the AMR, LiDAR, and a representative indoor world.

- Working SLAM pipeline (slam_toolbox) producing saveable occupancy grid maps in sim and hardware.

- Working AMCL localization on saved maps with error < 10 cm.

- Fully configured Nav2 stack tuned for the platform's geometry and dynamics.

- Unified agv_navigation.launch.py that brings up the full stack with one command.

### Supporting Deliverables

- URDF model with correct TF tree (map → odom → base_link → laser).

- Architecture diagram (nodes, topics, frames).

- README with installation, calibration, and operation instructions.

- Test report covering mapping, localization, and navigation success rates.

- Demonstration video (3–5 min) of mapping → save → autonomous navigation.

### New in v2 — C++ Learning Track Deliverables

- Standalone non-ROS C++ exercises in ~/C_learning/ (Git-tracked): differential-drive kinematics class, CMake-built PID controller.

- agv_cpp_learning ROS 2 package (ament_cmake) with five progression nodes: talker, listener, parameterized publisher, TF broadcaster, odom subscriber.

- Production C++ node udp_bridge_node.cpp — a drop-in replacement for the Python original, validated against it on real hardware.

- C++ learning journal (Markdown) capturing lessons, mistakes, and reference patterns.

## 1.4  Scope

### In Scope

- PC-side ROS 2 Jazzy software stack (Python and C++ nodes).

- Gazebo Harmonic simulation using ros_gz_bridge.

- Parameter tuning for Nav2, slam_toolbox, and AMCL.

- ESP32 firmware integration via UDP (odometry, cmd_vel) and TCP (LiDAR tunnel).

- 2D occupancy grid mapping and navigation in a static indoor environment.

- C++ for ROS 2 learning track: non-ROS foundations, rclcpp progression nodes, production hardware C++ node.

### Out of Scope

- Electrical and mechanical redesign of the robot.

- ESP32 firmware modification beyond minor parameter changes.

- 3D mapping, outdoor operation, multi-floor navigation.

- Multi-robot coordination or fleet management.

- IMU sensor fusion (robot_localization EKF) — deferred.

- Comprehensive C++ language mastery beyond the ROS 2 context (move semantics in depth, concurrency primitives, template metaprogramming, custom allocators, coroutines) — explicitly outside G5.

- Custom Nav2 plugins (costmap layers, planners, controllers) — possible with stretched C++ skills but not required.

## 1.5  Benefits and Costs

### Benefits

- Direct learning in two stacks: ROS 2 navigation and C++ for robotics.

- Employable dual-language competence: Python for prototyping, C++ for production and plugin work.

- Portfolio with working AMR plus a documented C++ learning journey.

- Foundation for thesis/capstone research (multi-robot, vision, plugins all require C++).

- Reproducibility: documented stack reusable for future student projects.

### Costs

| Cost Category | Estimate | Notes |
| --- | --- | --- |
| Hardware (sunk, owned) | ~ 6,000,000 VND | ESP32, RPLIDAR, motors, chassis, batteries. |
| Development PC | Already available | Ubuntu 24.04 workstation. |
| Software | 0 VND | All open source. |
| Labor — main project | ~ 300 hours | ≈ 15 h/week × 20 weeks. |
| Labor — C++ learning track | ~ 100 hours | ≈ 5 h/week × 20 weeks (weekends). |
| Contingency (parts, cables) | ~ 500,000 VND | Replacements. |
| TOTAL incremental cost | ~ 500,000 VND | Out-of-pocket. |
| TOTAL opportunity cost | ~ 400 hours | Student time across both tracks. |

## 1.6  Project Team & Stakeholders (RACI)

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity / Deliverable | Student | Advisor | Peers | Community |
| --- | --- | --- | --- | --- |
| Requirements & scope definition | R / A | C | I | – |
| Simulation development | R / A | C | C | I |
| SLAM mapping and tuning | R / A | C | I | C |
| Nav2 tuning and integration | R / A | C | I | C |
| Hardware bring-up and field testing | R / A | C | C | – |
| C++ learning track (new) | R / A | I | C | C |
| Documentation and final report | R / A | C | I | – |
| Project review and approval | R | A | I | – |

## 1.7  Project Success Criteria

SC1–SC7 carried from v1. New SC8–SC10 cover the C++ learning goal (G5).

| ID | Criterion | Target | Measurement Method |
| --- | --- | --- | --- |
| SC1 | Map completeness | ≥ 95% floor area | Manual comparison vs. floor plan. |
| SC2 | Map accuracy (wall thickness) | < 5 cm | Measure wall pixels in .pgm. |
| SC3 | AMCL localization error | < 10 cm at rest | Ground-truth vs. AMCL over 10 runs. |
| SC4 | Navigation goal success rate | ≥ 90% of 10 goals | Counted in test script. |
| SC5 | Obstacle avoidance | 0 collisions in test | Visual observation. |
| SC6 | System startup reliability | ≥ 95% clean bring-ups | 10 consecutive launches. |
| SC7 | Documentation completeness | README + arch. + demo | Peer review checklist. |
| SC8 | Non-ROS C++ foundations complete | 2 programs build & run | Kinematics class + PID class compile with CMake and pass self-tests. |
| SC9 | rclcpp progression nodes complete | 5 nodes in agv_cpp_learning | Talker, listener, parameter node, TF broadcaster, odom subscriber — each runnable and verified. |
| SC10 | Production C++ UDP bridge parity | Matches Python on 1-hour test | Same /odom and /tf output within floating-point tolerance on identical ESP32 packet stream. |

## 1.8  Risks and Mitigation

R1–R7 carried from v1. R8–R10 are new for v2.

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Nav2 tuning overruns | High | High | Strict 2-week time-box; use proven DWB defaults first. |
| R2 | Encoder odometry drift corrupts maps | High | Med | Calibrate empirically; rely on LiDAR scan-matching. |
| R3 | TF tree errors cause silent failures | Med | High | Verify with tf2_tools after every integration milestone. |
| R4 | WiFi latency disrupts real-time control | Med | High | Dedicated 5 GHz AP; firmware watchdog. |
| R5 | ROS 2 package breakage after apt upgrade | Low | High | Snapshot environment before each phase. |
| R6 | Hardware component failure | Low | High | Spares on hand; sim path stays productive. |
| R7 | Scope creep from stretch goals | Med | Low | Scope frozen Week 2; stretch goals parked. |
| R8 | C++ rewrite of working nodes destabilizes main project | Low | High | Python nodes remain authoritative until Week 20. C++ port is parallel and must be validated against Python before swap. |
| R9 | C++ learning exceeds 5 h/week budget | High | Low | Track is off critical path. If blocked, pause C++ and continue main project; catch up later or descope task 4.5. |
| R10 | Production C++ bridge has bugs the Python version lacks | Med | Med | Python version stays on disk as fallback. Parity required before swap. If C++ fails, project ships with Python; G5 partially met via agv_cpp_learning alone. |

## 1.9  Key Milestones

M1–M9 are main-project milestones. L1–L3 are C++ learning-track gates.

| ID | Milestone | Target Week | Acceptance Criterion |
| --- | --- | --- | --- |
| M1 | Charter approved, environment ready | Week 2 | Ubuntu + ROS 2 Jazzy + Gazebo Harmonic + Git + GitHub verified. |
| M2 | URDF complete, robot spawns in Gazebo | Week 6 | Robot visible in Gazebo with correct TF tree in RViz2. |
| M3 | Teleop + LiDAR in sim | Week 8 | Robot drives; /scan visible; /odom correct. |
| L1 | Non-ROS C++ foundations complete | Week 8 | Kinematics + PID classes compile and run; committed to ~/C_learning. |
| M4 | SLAM mapping works in sim | Week 12 | Complete 2D map saved from Gazebo world. |
| M5 | AMCL localizes in sim | Week 14 | Pose error < 10 cm on saved sim map. |
| L2 | rclcpp progression nodes complete | Week 14 | 5 nodes running in agv_cpp_learning; TF broadcaster verified vs. Python bridge. |
| M6 | Nav2 navigation works in sim | Week 16 | ≥ 8 of 10 goals reached without collision. |
| M7 | Hardware mapping complete | Week 20 | Physical map saved of target room. |
| L3 | Production C++ UDP bridge at parity | Week 20 | C++ bridge outputs match Python on live hardware for 1 hour. |
| M8 | Hardware navigation validated | Week 22 | SC1–SC6 met on hardware. |
| M9 | Project complete, repository published | Week 24 | Docs reviewed; demo video recorded; all three repos public. |

## 1.10  Assumptions and Constraints

### Assumptions

- ESP32 firmware interface does not change during the project.

- WiFi is reliable on 5 GHz in the lab.

- Student has ~20 hours/week total (15 main + 5 C++) for 24 weeks.

- Representative indoor test environment is accessible.

### Constraints

- ROS 2 Jazzy Jalisco only (not Humble, Kilted, Rolling).

- Gazebo Harmonic only.

- Differential-drive only.

- Hardware budget ≤ 500,000 VND.

- Individual project — no additional developers.

- C++ track must never preempt main-project work. If both are due and time is short, main project wins.

# Part 2 — Project Schedule

## 2.0  Repository & Folder Layout

The project spans three independent Git repositories, each with a clear purpose. Keeping them separate prevents C++ learning churn from polluting the production package history and lets each be cloned, reviewed, or published on its own.

| Path on disk | Repository purpose | Build system |
| --- | --- | --- |
| ~/C_learning/ | Standalone C++ exercises (pre-ROS). Kinematics class, PID, CMake practice. | Plain g++ or minimal CMake. NOT a ROS workspace. |
| ~/ros2_ws/src/agv_cpp_learning/ | rclcpp learning package. 5 progression nodes building toward the production bridge. | ament_cmake (ROS 2 C++ package). |
| ~/ros2_ws/src/agv_base_controller/ | PRODUCTION package — the actual AMR project deliverable. | ament_python (Jazzy default; may migrate to ament_cmake_python at Week 17 for the C++ bridge). |

~/ros2_ws itself is NOT a Git repo. Each of the three repos above is self-contained. The two learning repos may be public from day one; the production repo goes public at M9.

## 2.1  Work Breakdown Structure (WBS)

Six work packages. 1.0–5.0 are the main project. 6.0 is the new C++ learning track.

| WBS | Work Package / Task | Description |
| --- | --- | --- |
| 1.0 | Project Initiation |  |
| 1.1 | Charter & scope definition | Write charter v2; freeze scope. |
| 1.2 | Environment setup | Ubuntu 24.04, ROS 2 Jazzy, Gazebo Harmonic, VS Code, Git. |
| 1.3 | Git repository initialization | Create all three repos: C_learning, agv_cpp_learning, agv_base_controller. |
| 2.0 | Simulation Development |  |
| 2.1 | URDF authoring | Add inertials + Gazebo plugins for diff-drive and LiDAR. |
| 2.2 | Gazebo world creation | SDF world with walls and obstacles. |
| 2.3 | Gazebo plugin integration | ros_gz_bridge config; verify /scan and /odom in sim. |
| 2.4 | Simulation teleop validation | Drive with teleop_twist_keyboard; verify topics. |
| 3.0 | SLAM & Localization |  |
| 3.1 | slam_toolbox configuration | Tune params for LiDAR range and resolution. |
| 3.2 | Mapping runs in simulation | Build and save maps; verify quality. |
| 3.3 | AMCL configuration | Tune diff motion model + laser likelihood. |
| 3.4 | Localization validation | Convergence + accuracy on saved map. |
| 4.0 | Navigation (Nav2) |  |
| 4.1 | Nav2 core bring-up | controller, planner, behaviors, BT, lifecycle mgr. |
| 4.2 | Costmap tuning | Inflation, obstacle layer, robot_radius. |
| 4.3 | Controller tuning (DWB) | Match v, ω, accel limits to platform. |
| 4.4 | Full stack validation in sim | 10-goal test; success rate + time-to-goal. |
| 4.5 | Production C++ udp_bridge_node.cpp | Port Python bridge to C++; validate parity (depends on 6.x). |
| 5.0 | Hardware Integration & Closeout |  |
| 5.1 | ESP32 + PC network validation | UDP odom + TCP LiDAR on real WiFi. |
| 5.2 | Real-world mapping | Map target lab room with slam_toolbox. |
| 5.3 | Real-world navigation | Nav2 on hardware; validate SC1–SC6. |
| 5.4 | Documentation finalization | README, arch diagram, operation guide. |
| 5.5 | Demo video & project handoff | Record 3–5 min demo; publish all repos. |
| 6.0 | C++ Learning Track (new) | Parallel, off-critical-path |
| 6.1 | Non-ROS C++ warm-up | Differential-drive kinematics class (Week 3). |
| 6.2 | CMake practice | Split kinematics into library + executable; PID class (Week 4). |
| 6.3 | rclcpp talker + listener | First contact with ament_cmake (Weeks 7–8). |
| 6.4 | Params + timers + YAML config | Real-world rclcpp patterns (Weeks 11–12). |
| 6.5 | TF2 broadcaster in C++ | Consume /odom from Python bridge (Weeks 13–14). |
| 6.6 | Odom subscriber + POSIX sockets | Final primitives for the capstone (Weeks 15–16). |
| 6.7 | Capstone prep & Nav2 source reading | Review all sandbox nodes; study Nav2 C++ examples (Weeks 17–18). |
| 4.5 = 6.8 | Production port (capstone) | Match Python bridge behavior on hardware (Weeks 19–20). |

## 2.2  Task List with Durations and Dependencies

★ = critical path. Purple rows are C++ learning tasks — none are on the critical path.

| WBS | Task | Duration | Predecessor | Owner | Critical? |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Charter v2 & scope | 1 w | — | Student | ★ |
| 1.2 | Environment setup | 1 w | 1.1 FS | Student | ★ |
| 1.3 | Git init (3 repos) | 0.5 w | 1.1 FS | Student |  |
| 2.1 | URDF authoring | 2 w | 1.2 FS | Student | ★ |
| 2.2 | Gazebo world | 1 w | 1.2 FS | Student |  |
| 2.3 | Gazebo plugins | 2 w | 2.1, 2.2 FS | Student | ★ |
| 2.4 | Teleop validation | 2 w | 2.3 FS | Student | ★ |
| 3.1 | slam_toolbox config | 2 w | 2.4 FS | Student | ★ |
| 3.2 | Mapping runs (sim) | 2 w | 3.1 FS | Student | ★ |
| 3.3 | AMCL config | 1 w | 3.2 FS | Student | ★ |
| 3.4 | Localization validation | 1 w | 3.3 FS | Student | ★ |
| 4.1 | Nav2 core bring-up | 1 w | 3.4 FS | Student | ★ |
| 4.2 | Costmap tuning | 1 w | 4.1 FS | Student | ★ |
| 4.3 | DWB controller tuning | 1 w | 4.2 FS | Student | ★ |
| 4.4 | Full sim validation | 1 w | 4.3 FS | Student | ★ |
| 5.1 | Network validation | 1 w | 4.4 FS | Student | ★ |
| 5.2 | Real-world mapping | 1 w | 5.1 FS | Student | ★ |
| 5.3 | Real-world navigation | 2 w | 5.2 FS | Student | ★ |
| 5.4 | Documentation | 1 w | 5.3 FS | Student | ★ |
| 5.5 | Demo & handoff | 1 w | 5.4 FS | Student | ★ |
| 6.1 | Non-ROS C++ warm-up | 1 w | 1.3 FS | Student |  |
| 6.2 | CMake practice | 1 w | 6.1 FS | Student |  |
| 6.3 | rclcpp talker + listener | 2 w | 6.2 FS | Student |  |
| 6.4 | Params + timers + YAML | 2 w | 6.3 FS | Student |  |
| 6.5 | TF2 broadcaster | 2 w | 6.4 FS | Student |  |
| 6.6 | Odom sub + POSIX sockets | 2 w | 6.5 FS | Student |  |
| 6.7 | Capstone prep | 2 w | 6.6 FS | Student |  |
| 4.5 | Production C++ bridge port | 2 w | 6.7, 5.1 FS | Student |  |

## 2.3  Gantt Chart (Week-by-Week)

Blue bars = main-project tasks. Purple bars = C++ learning tasks. Orange cells on the bottom row = milestones. Each C++ block sits in a natural lull of the main project (URDF review weeks, tuning weeks). The C++ capstone (task 4.5) runs in Weeks 19–20, slotted between hardware mapping and hardware navigation validation.

| WBS | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Charter v2 & scope |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Environment setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Git init (3 repos) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | URDF authoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | Gazebo world |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Gazebo plugins |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 | Teleop validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | slam_toolbox config |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Mapping runs (sim) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | AMCL config |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 | Localization validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Nav2 core bring-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 | Costmap tuning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 | DWB controller tuning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4 | Full sim validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Network validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 | Real-world mapping |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 | Real-world navigation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 | Documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5 | Demo & handoff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Non-ROS C++ warm-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 | CMake practice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 | rclcpp talker + listener |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.4 | Params + timers + YAML |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.5 | TF2 broadcaster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.6 | Odom sub + POSIX sockets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.7 | Capstone prep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.5 | Production C++ UDP bridge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| — | Milestones |  | M1 |  |  |  | M2 |  | M3/L1 |  |  |  | M4 |  | M5/L2 |  | M6 |  |  |  | M7/L3 |  | M8 |  | M9 |

Legend: ■ Blue = main-project task.  ■ Purple = C++ learning task.  ■ Orange = milestone. Labels like 'M3/L1' indicate both a main milestone and a C++ learning-track gate that week.

## 2.4  Critical Path Analysis

The main-project critical path is unchanged from v1:

1.1 → 1.2 → 2.1 → 2.3 → 2.4 → 3.1 → 3.2 → 3.3 → 3.4 → 4.1 → 4.2 → 4.3 → 4.4 → 5.1 → 5.2 → 5.3 → 5.4 → 5.5

Total critical path duration: 24 weeks. The C++ track (6.1–6.7) sits OFF the critical path. Task 4.5 depends on 6.7 and 5.1 but does not precede 5.3: if 4.5 slips, the project ships with the Python bridge and still meets all main-project success criteria. Goal G5 then becomes partially met (SC8 and SC9 achieved; SC10 postponed).

### C++ track scheduling principle

Each C++ task lands in a calendar week where the main project is in a consolidation state — URDF review, parameter tuning, map recording — activities where the student is often blocked on thinking or waiting rather than coding. The 5 h/week budgeted for the C++ track is the time that would otherwise be spent re-reading documentation; the track replaces that loose time with structured practice.

### Fallback escalation rules

- If any main-project milestone slips > 1 week, PAUSE the C++ track and redirect all hours to the main project.

- If L1 slips > 2 weeks, descope 6.5 and 6.6 (keep only rclcpp basics).

- If L2 slips > 2 weeks, descope task 4.5 entirely; project ships with Python bridge.

- If L3 cannot be achieved by Week 22, mark G5 as partially achieved; the progression nodes still count.

## 2.5  Schedule Assumptions & Buffers

- Student delivers 15 h/week on main project + 5 h/week on C++ track = 20 h/week total.

- C++ hours come primarily from weekend mornings; evening hours stay with the main project.

- No vacation or exam periods currently factored — add 1–2 week buffer if an exam overlaps.

- Week 24 contains ~20% buffer implicit in its documentation tasks.

- The 1-week gap between Weeks 19–20 (C++ port) and Week 21 (hardware navigation) is intentional float.

# Approvals

By signing below, the student and advisor confirm that this v2 charter represents the agreed-upon scope, goals (including G5), success criteria, and schedule for the AMR development project.

| Role | Signature / Date |
| --- | --- |
| Student (Project Owner) | ______________________________ |
| Academic Advisor | ______________________________ |